## Risk
№ | Classification | Condition | Effects | Reaction | The likelihood of risk (%) | The severity of the risk (1-10) | Prevention
1 | People | Work on the project is irregular | The project will exit the project schedule and will not be fully completed by the deadline | Allocate extra time to work on the project outside of working hours | 20% | 5 | Teamwork during scheduled meetings
2 | People | Due to lack of experience, the project plan is not well thought out | The project will exit the project schedule and will not be fully completed by the deadline | Expert advice | 10% | 4 | The study of additional literature
3 | People | Due to lack of experience, the project does not according to the requirements of the customer | The project will be a failure | Try to arrange with the customer | 20% | 8 | Notify the customer in advance of their capabilities
4 | People | During work on the project, conflicts arise in the team | Possible poorly executed work and the probability of not meeting the deadline | Try to resolve conflicts | 7% | 3 | More thoughtful pick a team
5 | People | While working on a project one or more employees are fired | The remaining employees will have to do more work | Try to find a replacement, redistribute the work of the resigned as thoughtfully as possible | 25% | 6 | Arrange with other employees
6 | People | Unforeseen expenses arise during project execution | The project will become problematic and losses may occur | Contact the customer and try to cut costs | 15% | 4 | Anticipate such a situation in advance and deposit the estimated amount in advance.
7 | People | While working on a project, one or more employees become ill | The remaining other employees will have to do more work | Try to find a replacement, redistribute the work of the resigned as thoughtfully as possible | 35% | 5 | Arrange with other employees
8 | People | The customer does not contact for several days | You may not have time to approve the specifications for the next phase on time, the project will exit the project schedule | Try to contact the customer through his subordinates | 20% | 2 | To inform the customer that the responsibility for any delays caused by his absence lies with him
9 | People | Leakage of confidential data | Loss of intellectual property and use of confidential information for purposes that could harm the business | Try to eliminate the consequences | 20% | 7 | Classification of data by degree of confidentiality and differentiation of access to them; storage of especially important information on separate media with enhanced protection
10 | People | For internal reasons of the company, the customer abandons the project | The project will be a failure and large financial losses are possible. | Try to compromise | 15% | 7 | Coordination with the customer of the consequences of this risk
11 | Technical equipment | Equipment breakdown/failure | The project will exit the project schedule and will not be fully completed by the deadline | Repair equipment or search for its replacement | 25% | 7 | Data synchronization as the project progresses between multiple PCs
12 | Technical equipment | During implementation, the software product does not work on customers equipment | The project will exit the project schedule, there may be losses | Modify a software product for correct operation on customer equipment | 15% | 3 | To organize remote testing of a software product on customer equipment at the testing stage
13 | Technical equipment | The size of the software product is much larger than calculated | The software product cannot be implemented | Try to make the software more compact | 25% | 6 | During the development of the project, take into account the calculated characteristics of the software product
14 | Software environment | During work on the project, electricity is turned off for several days | The project will exit the project schedule and will not be fully completed by the deadline | Try to establish energy supply and find an alternative | 15% | 4 | Purchase additional energy sources